INTERNAL DETAILED COST BREAKDOWN

INTERNAL ONLY

| Client | Linda Bushel | Project | Bushel Rear Deck (pool deck) |
| --- | --- | --- | --- |
| Site | 12 D'Arcy's Way, Kemptville, ON K0G 1J0 | Date | 2026-10-27 |

| Material / Package | Direct Cost | Status |
| --- | --- | --- |
| Framing lumber — BMR estimate 237147/1 | $1,361.71 | Written quote; Darcy's price is Brayman's cost. EXPIRES 28 OCT 2026 — confirm/order promptly |
| Structural hardware — BMR | $389.35 | Written quote |
| Trex Select Island Mist decking — BMR | $4,827.20 | Written quote |
| Trex Island Mist fascia — BMR | $1,666.80 | Written quote |
| Trex fasteners and fascia screw kit — BMR | $431.03 | Written quote |
| Vista 42 in railing and gate — quote 87915-165209 | $3,851.49 | Written quote, ADDITIONAL to BMR (Joel confirmed). Quoted price is Brayman's cost |
| Helical piles, 11 — Pro Post OT-2236, SUPPLY AND INSTALL | $3,265.00 | Written quote; installation included, so no Brayman pile labour. 11 piles govern; J1 15-pier evidence kept. QUOTE EXPIRED 21 OCT — reconfirm before commitment |
| Pro Post travel fee | $85.00 | Written quote |
| Pro Post engineer report and compliance letter | $400.00 | Written quote. Included as quoted; required if the town asks |
| Delivery and carrying — BMR | $0.00 | BMR: extra; no amount on any document. Absorbed |
| Equipment | $0.00 | None: Pro Post brings its own machine |
| Town permit fee | Excluded | Not in the customer price; billed at cost |
| Total materials and subcontract | $16,277.58 | BMR $8,676.09 + Vista $3,851.49 + Pro Post $3,750.00 |

# Labour by Task

| Task | Hours | Direct Cost |
| --- | --- | --- |
| Layout and mark the pile locations | 4 | $300.00 |
| Posts and beams | 16 | $1,200.00 |
| Upper-deck framing | 24 | $1,800.00 |
| Lower-deck framing | 8 | $600.00 |
| Stairs | 16 | $1,200.00 |
| Trex decking | 16 | $1,200.00 |
| Stair treads and risers (Trex) | 8 | $600.00 |
| Trex fascia | 5 | $375.00 |
| Railing blocking | 4 | $300.00 |
| Vista railing and gate | 16 | $1,200.00 |
| Unload and carry materials | 4 | $300.00 |
| Clean-up and final walk-through | 4 | $300.00 |
| Total Brayman labour at $75.00 per man-hour | 125 | $9,375.00 |

# Pricing Reconciliation

| Component | Amount |
| --- | --- |
| Materials and subcontract | $16,277.58 |
| Brayman labour (125 man-hours × $75.00) | $9,375.00 |
| Total direct cost | $25,652.58 |
| Pricing method | True gross margin 15% (not markup): selling price = direct cost ÷ 0.85 |
| Gross profit | $4,526.93 |
| Selling price before HST | $30,179.51 |
| HST 13% | $3,923.34 |
| Total including HST | $34,102.85 |
| Resulting true gross margin | 15.00% |
| Quote status | BMR/Darcy pricing expires 28 Oct 2026 — confirm/order promptly. Pro Post OT-2236 expired 21 Oct — reconfirm before commitment |
| Status | For Ben's review. Customer estimate not sent to Linda |

Direct costs, labour hours, supplier values, and quoted totals are project-specific and are not stored in this reusable master.